BOOOM MORE

MVP Plan: 3 Weeks

Week-by-week build plan  |  Development budget: $200  |  Draft, 28 September 2026

# 1. What we are building

We will build BOOOM More exactly as described in the client's brief and shown in the demo screens: one workspace where a user goes from a business idea to a ready campaign package (audience, campaign direction, ad copy, budget, and export).

This is an MVP. That means all parts of the brief are built and working from start to end, but each part is kept simple and basic. No extra features. Deeper improvements come later in Phase 2.

# 2. Plan at a glance

| Week | Focus | What the client can see at the end |
| --- | --- | --- |
| Week 1 | Foundation, login, dashboard, campaign brief | Sign in, create a project, fill the brief, save it and come back later |
| Week 2 | AI engine, audience, campaign directions, creative workspace | Brief turns into audience options, 3 campaign directions, and editable ad assets |
| Week 3 | Budget, conversions, export, landing page, testing, going live | Full flow works end to end and is live online for the client to try |

# 3. Week 1: Foundation and Campaign Brief

Goal: set up the base of the app and finish the first stage of the user flow.

Work in this week

- Project setup, code repository, database, and hosting setup (Vercel for the app, Render for the backend, Supabase or Neon for database and files)

- Sign up and login (one owner per workspace)

- Dashboard: create project, continue a draft, duplicate, delete, see status and last edited

- Settings page: account, privacy, export data, delete project (billing is a placeholder only)

- Campaign Brief form with all fields from the client brief, required-field marks, and autosave

- Logo and reference file upload with basic file checks

- AI summary of the brief so the user can review and confirm the facts before generating

By end of week: A user can sign in, create a project, fill and save the brief, leave, and continue later without losing anything.

# 4. Week 2: AI Engine and Creative Work

Goal: build the AI part and the three middle stages of the flow.

Work in this week

- AI generation steps: brief summary, audience, campaign directions, assets. Each step is saved as structured data

- Generation runs in the background, so a page refresh does not lose it. Failed steps can be retried, and existing work is never erased

- Identify Target: 2 to 4 audience cards with need, motivation, objection, message angle, channels, and "based on" labels. User can edit, pick one, add exclusions, or write their own

- Generate Campaign: 3 different directions to compare, choose, edit, or regenerate one at a time, with a short history so nothing is lost

- Creative Workspace tabs: overview, landing page outline, short ad copy, long ad copy, email, social post, visual production brief

- In each asset: edit fields, regenerate one field only, save version, restore old version, copy, and approve

- Basic AI safety: AI does not invent prices or results, and risky claims (health, finance, performance) are flagged for review

By end of week: A brief turns into audience options, three campaign directions, and editable ad assets, and one asset can be regenerated without touching the rest.

# 5. Week 3: Budget, Conversions, Export, and Launch

Goal: finish the last three stages of the flow, add the landing page, then test and go live.

Day-by-day plan

- Days 1 to 2, Allocate Budget: recommended split by channel with amounts and percentages, lock a channel and rebalance the rest, total always matches the budget, assumptions shown, media and production cost kept separate

- Day 3, Manage Conversions: goal, landing destination, tracking checklist, review schedule, and manual entry of spend, leads, sales, and revenue with simple calculations (like cost per lead) and clear messages when data is missing

- Day 4, Review and Export: approval checklist, PDF export, editable Word or text export, copy single assets, version label and date, and a clear "Not published" status

- Day 5, Landing page: the four capabilities, sample output, and call to action

- Day 6, Testing: run the full flow on a laptop and on a phone browser (layout, buttons, forms), check labels and contrast, fix bugs

- Day 7, Go live and handover: final deployment, source code, and a short README

By end of week: The complete flow, from brief to export, works on a laptop and in a phone browser, and is live online.

# 6. MVP level: what "basic" means here

| Area | In this MVP |
| --- | --- |
| Design | Follows the client's demo screens (dark theme, same layout). Simple loading feedback, no special animation |
| Login | Email and password, one owner role |
| Security | Secure connection, private projects, secrets kept on the server, upload checks, basic rate limits |
| Accessibility | Keyboard use, labels, and contrast checked on main flows. Full audit comes later |
| Tracking | Basic event counts only |
| Language and market | English and US |
| Hosting | Vercel (app), Render (backend), Supabase or Neon (database and files). Free or low-cost plans for the MVP |
| Phone support | Same web app opens in a phone browser and works there. No separate mobile app |

# 7. Not in this MVP (Phase 2)

- Live ad account or analytics connections, auto posting, and any ad spend

- Finished AI-generated images (we provide image directions and visual briefs only)

- Budget forecasts, real billing and payments, team roles and approvals

- Native mobile apps and other languages

- Full accessibility audit, advanced monitoring, and the 5 to 10 user pilot test

- Vector logo redesign (client provides the logo files)

- Moving the app to AWS or any other hosting later (separate, paid task)

# 8. What we need from the client

- Confirmation that the MVP is hosted on our setup (Vercel, Render, Supabase or Neon), not on the client's AWS

- Who pays for hosting if free plans are not enough once real users arrive

- AI API key (Anthropic or OpenAI) or credits. AI usage cost is not part of the $200

- Logo files and confirmation that we can use them

- Feedback within 1 to 2 days at the end of each week, so the schedule stays on track

- Any new request outside this document is treated as Phase 2

# 9. Deliverables

- Working web app live online (Vercel + Render)

- Full source code

- Short README for setup and running

- One round of bug fixes within 3 days after handover

# 10. Budget and after launch

Development budget for this MVP: $200. Suggested payment: 50% before starting, 50% on delivery, or as agreed in writing.

Maintenance, upgrades, and Phase 2 features are a separate paid engagement, agreed after the MVP is delivered.